## Project Planner
FoodDB Project
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
1 - Initiation Process Group | 1 | 5 | 1 | 5 | 100%
1.1 - Draw Project Charter | 1 | 1 | 1 | 1 | 100%
1.1.1 - Problem Background | 2 | 1 | 2 | 1 | 100%
1.1.2 - High-level System Capabilities | 3 | 1 | 3 | 1 | 100%
1.1.3 - Benefit Analysis | 4 | 1 | 4 | 1 | 100%
1.2 - Identify Stakeholders | 5 | 1 | 5 | 1 | 100%
2 - Planing Process Group | 6 | 18 | 6 | 18 | 100%
2.1 - Gather Requirements | 6 | 3 | 6 | 3 | 100%
2.2 - Establish Scope | 9 | 2 | 9 | 2 | 100%
2.2.1 - Functional Requirements | 11 | 5 | 11 | 5 | 100%
2.2.1.1 - User Requirements | 11 | 1 | 11 | 1 | 100%
2.2.1.2 - Software Requirements | 12 | 2 | 12 | 2 | 100%
2.2.1.3 - Use Cases and Use Case Diagrams | 14 | 1 | 14 | 1 | 100%
2.2.1.4 - Software Design Choices | 15 | 1 | 15 | 1 | 100%
2.2.2 - Non-Functional Requirements | 16 | 3 | 16 | 3 | 100%
2.2.2.1 - Structural Design | 16 | 1 | 16 | 1 | 100%
2.2.2.2 - Visual Design Choices | 17 | 2 | 17 | 2 | 100%
2.3 - Create Project Management Plan | 19 | 5 | 19 | 5 | 100%
2.3.1 - Define and Sequence Activities | 19 | 2 | 19 | 2 | 100%
2.3.2 - Estimate Activity Resources | 21 | 1 | 21 | 1 | 100%
2.3.3 - Create WBS | 22 | 1 | 22 | 1 | 100%
2.3.4 - Create Gantt Chart | 23 | 1 | 23 | 1 | 100%
3 - Executing Process Group | 24 | 14 | 24 |  | 0%
3.1 - Assign Work Based Off Plan | 24 | 1 | 24 | 1 | 100%
3.2 - Develop Project | 25 | 7 |  |  | 0%
3.2.1 - Test Project During Development | 32 | 2 |  |  | 0%
3.3 - Conduct Meetings | 34 | 2 |  |  | 0%
3.4 - Monitor Risks | 36 | 1 |  |  | 0%
3.5 - Frequently Update Plan Based Off Events and Progress | 37 | 1 |  |  | 0%
4 - Monitoring and Controlling Process Group | 38 | 9 |  |  | 0%
4.1 - Monitor Development of Project | 38 | 3 |  |  | 0%
4.1.1 - Control Scope | 38 | 1 |  |  | 0%
4.1.2 - Control Quality | 39 | 1 |  |  | 0%
4.1.3 - Control Resources | 40 | 1 |  |  | 0%
4.2 - Assess Risks Over Time | 41 | 2 |  |  | 0%
4.3 - Update Plans | 43 | 2 |  |  | 0%
4.4 - Report Progress to Relevant Stakeholders | 45 | 2 |  |  | 0%
5 - Closing Process Group | 47 | 3 |  |  | 0%
5.1 - Review Performance | 47 | 1 |  |  | 0%
5.2 - Create Final Report | 48 | 2 |  |  | 0%